# BIA Right-of-Way Readiness Checklist

For broadband projects on tribal land and individually owned Indian land under 25 CFR Part 169

General information, not legal advice. This is an editable starting point, not a legal form. Work with your BIA (Bureau of Indian Affairs) Agency realty office and your tribal legal counsel on every project, and check the current 25 CFR (Code of Federal Regulations) Part 169 on eCFR (the Electronic Code of Federal Regulations, www.ecfr.gov) before you act. Rules and policies change.

# How to use this checklist

Go through this list with your realty, planning, utility, and legal staff before you send a right-of-way (ROW) package to BIA. Check each box when the item is done, and use the Notes column for dates, names, and file locations. Section numbers refer to 25 CFR Part 169 unless noted. Use one checklist per application.

# Project information

| Item | Fill in |
| --- | --- |
| Project name |  |
| Applicant (utility or company) |  |
| Tribe |  |
| BIA Agency and realty contact |  |
| Route description (from and to) |  |
| Number of tracts |  |
| Tribal legal counsel |  |
| Date this checklist was started |  |

# 1. Before you apply

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Route drawn on a map; every tract it crosses is listed | Planning step |  |
| ☐ | Land status known for each tract: tribal land, individually owned Indian land, BIA land, fee land, or road | 169.2, 169.3 |  |
| ☐ | Fee land identified; permission from fee owners handled outside the BIA process | 169.3(b) |  |
| ☐ | State or county roads identified; road owner contacted | Ask the Agency |  |
| ☐ | Existing leases, permits, and tribal land assignments checked for uses they already allow | 169.4(b)(2) |  |
| ☐ | Grants under special acts of Congress, or tracts where one Indian landowner owns 100%, discussed with BIA and counsel | 169.1(d), 169.4(b)(1) |  |
| ☐ | Tower sites, buildings, and access points flagged for a possible business lease | 25 CFR 162, Subpart D |  |
| ☐ | Home and building drops flagged for service line agreements | 169.51 to 169.56 |  |
| ☐ | Title Status Reports requested for each tract | Ask the Agency |  |
| ☐ | Written request to BIA for owner names, addresses, and shares | 169.106 |  |
| ☐ | Landowner consent to survey obtained (BIA approval not needed) | 169.101 |  |
| ☐ | Asked the Agency whether NPM-TRUS-48 or a newer policy memo is in effect | NPM-TRUS-48 |  |
| ☐ | Asked the Agency how to submit: mail, email, or both | Ask the Agency |  |

# 2. Application contents (169.102)

There is no required form (169.102(c)). BIA publishes an optional form (OMB 1076-0181, an Office of Management and Budget control number) and a checklist. A complete package includes each item below.

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | The tracts the right-of-way crosses | 169.102 |  |
| ☐ | The purpose of the right-of-way (for example, a buried fiber line) | 169.102, 169.5 |  |
| ☐ | The duration requested | 169.102, 169.201 |  |
| ☐ | A legal description of the right-of-way | 169.102 |  |
| ☐ | A map of definite location | 169.102 |  |
| ☐ | Security: bond or other security, or a waiver or exemption | 169.102, 169.103 |  |
| ☐ | Proof of notice to the landowners | 169.102, 169.107(b) |  |
| ☐ | Consents: tribal authorization and owners' written consents | 169.102, 169.107 |  |
| ☐ | Valuation, or a waiver of valuation | 169.102, 169.110, 169.112 |  |
| ☐ | Environmental and archaeological reports | 169.102, 169.123 |  |
| ☐ | Tribal conformance statement, if the tribe requires one | 169.102(b) |  |

# 3. Consents

## Tribal land

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Tribal authorization adopted (date and number in Notes) | 169.107(a) |  |
| ☐ | Written agreement signed, if the tribe requires one | 169.107(a) |  |
| ☐ | Tribe's conditions listed; they will become grant conditions | 169.107(a) |  |

## Individually owned Indian land (allotments)

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Notice sent to all owners; proof kept | 169.107(b) |  |
| ☐ | Written consents from owners of the majority interest (over 50% of shares) | 169.107(b) |  |
| ☐ | Owner count matches BIA records as of the application date | 169.107(c) |  |
| ☐ | Who may consent checked (for example, for minors or others who cannot sign for themselves) | 169.108 |  |
| ☐ | Life estates handled | 169.109 |  |
| ☐ | Fee shares left out of the consent count | 169.3(c) |  |
| ☐ | Tracts with 50 or more co-owners discussed with BIA; the four no-consent conditions reviewed (including 60 days' notice and a 30-day objection window) | 169.107(b)(1) and (2) |  |

# 4. Compensation

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Tribal land: amount negotiated, valuation waived by tribal authorization, or BIA asked for fair market value first | 169.110 |  |
| ☐ | Allotted land: at least fair market value, unless an exception applies | 169.112(a) |  |
| ☐ | Allotted land: request for nominal or reduced payment (tribal utility, utility cooperative that directly benefits the land, or written owner waiver) | 169.112(b) |  |
| ☐ | Allotted land: valuation waiver, if used | 169.112(c) |  |
| ☐ | Fair market value set for owners who did not consent | 169.112(d) |  |
| ☐ | Valuation method confirmed with BIA | 169.114 |  |

# 5. Environmental and cultural review

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Environmental, historic-preservation, and cultural-resource review planned with BIA | 169.123(a) |  |
| ☐ | NEPA (National Environmental Policy Act) documents ready for the package | 169.123(b) |  |
| ☐ | NHPA (National Historic Preservation Act) Section 106 review discussed | 169.123(a) |  |
| ☐ | ESA (Endangered Species Act) and other federal environmental laws checked | 169.123(a) |  |
| ☐ | Asked NTIA and BIA whether an NTIA (National Telecommunications and Information Administration) categorical exclusion fits | NTIA (2024) |  |
| ☐ | Extraordinary circumstances checked: traditional cultural properties, sacred sites, tribal law | NTIA (2024) |  |
| ☐ | For TBCP (Tribal Broadband Connectivity Program) projects, NTIA and BIA review coordination confirmed | NTIA (2022) |  |
| ☐ | Crews told to stop work if unreported cultural resources are found | 169.125(c)(4) |  |

# 6. Security and insurance

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Bond or other security arranged (no cash bonds) | 169.103, 169.103(j) |  |
| ☐ | Insurance names the landowners and the United States as additional insureds | 169.103(b) |  |
| ☐ | Waiver requested, if eligible (tribe's decision on tribal land; majority owners, tribal utility, or utility cooperative on allotted land) | 169.103(f) |  |
| ☐ | Government exemption claimed, if barred by law from posting security | 169.103(k) |  |

# 7. Submission and BIA review

| Item | Rule | Date |
| --- | --- | --- |
| Package sent; date BIA received it | 169.102 |  |
| BIA letter saying the package is complete | 169.123(b) |  |
| BIA decision due: 60 days after a complete package | 169.123(b) |  |
| BIA letter asking for more time (if any) | 169.123(b) |  |
| Decision due: 30 days after that letter | 169.123(b) |  |
| Notice to compel sent to the Regional Director (15 days to act) | 169.304 |  |
| Notice to compel sent to the BIA Director (15 days to act) | 169.304 |  |
| Appeal filed with the Interior Board of Indian Appeals (if needed) | 169.304 |  |
| Grant approved (effective date) | 169.301 |  |

Remember: a missed deadline does not mean the right-of-way is approved. BIA must grant unless it has a compelling reason not to (169.124).

# 8. After the grant

| Done | Item | Rule | Notes |
| --- | --- | --- | --- |
| ☐ | Grant recorded in the LTRO (Land Title and Records Office); copy in the project file | 169.301 to 169.302 |  |
| ☐ | Title Status Reports updated to show the right-of-way | 51 IAM 1-H |  |
| ☐ | Term and renewal dates on the calendar | 169.201 to 169.203 |  |
| ☐ | Any change of use (for example, copper to fiber) discussed with BIA before work starts | NPM-TRUS-48, 169.204 |  |
| ☐ | Assignments and mortgages only as the grant and BIA allow | 169.207, 169.210 |  |
| ☐ | Service line agreements filed with BIA within 30 days, with plats | 169.56 |  |
| ☐ | Contact named for notices of violation (10 business days to cure) | 169.404 |  |

# Notes and questions for the Agency

__________________________________________________________________

__________________________________________________________________

__________________________________________________________________

__________________________________________________________________

__________________________________________________________________

__________________________________________________________________

# References

Bureau of Indian Affairs. (n.d.). Apply for broadband right-of-way in Indian Country. https://www.bia.gov/service/broadband-access/apply-broadband-right-of-way

Bureau of Indian Affairs. (2022a). 51 IAM 1-H: Land titles and records handbook. https://www.bia.gov/sites/default/files/dup/assets/public/raca/handbook/pdf/51-iam-1-h_ltro-handbook_final_signed_508.pdf

Bureau of Indian Affairs. (2022b). 52 IAM 9-H: Rights-of-way (ROW) on Indian lands handbook. https://www.bia.gov/policy-forms/handbooks/52-iam-9-h-rights-way-row-indian-lands-handbook

Bureau of Indian Affairs. (2025). NPM-TRUS-48: Streamlining the rights-of-way application processes for broadband infrastructure projects across Indian trust and restricted land. https://www.bia.gov/sites/default/files/dup/assets/public/raca/national_policy_memoranda/pdf/npm-trus-48_streamlining-rows-broadband_final_signed_508.pdf

National Telecommunications and Information Administration. (2022, August 9). NTIA and BIA sign agreement to streamline environmental permitting for high-speed internet projects on tribal lands. https://broadbandusa.ntia.gov/news/latest-news/ntia-and-bia-sign-agreement-streamline-environmental-permitting-high-speed

National Telecommunications and Information Administration. (2024). Notice of newly adopted NEPA categorical exclusions. https://broadbandusa.ntia.gov/funding-programs/policies-waivers/Notice_of_Newly_Adopted_NEPA_Categorical_Exclusions

Rights-of-Way on Indian Land, 25 C.F.R. pt. 169 (2026). https://www.ecfr.gov/current/title-25/chapter-I/subchapter-H/part-169

Rights-of-Way on Indian Land, 80 Fed. Reg. 72492 (November 19, 2015). https://www.federalregister.gov/documents/2015/11/19/2015-28548/rights-of-way-on-indian-land

Rights-of-Way on Indian Land, 81 Fed. Reg. 14976 (March 21, 2016). https://www.gpo.gov/fdsys/pkg/FR-2016-03-21/html/2016-06269.htm

Rights-of-Way on Indian Land; Bond Exemption, 84 Fed. Reg. 42806 (August 19, 2019). https://www.govinfo.gov/content/pkg/FR-2019-08-19/html/2019-17781.htm