## Read Me
ROW Project Tracker: BIA rights-of-way for broadband
Numu Communications Learning Center. Free to use and adapt; please keep this credit.
General information, not legal advice. Work with your BIA (Bureau of Indian Affairs) Agency realty office and tribal legal counsel, and check the current 25 CFR (Code of Federal Regulations) Part 169 on eCFR (www.ecfr.gov). Rules and policies change.
How to use this workbook
Tracts: one row per tract the route crosses. Pick the land status from the list. The sheet fills in who must consent and checks for a majority interest.
Timeline: enter planned and actual dates. Gray deadline cells calculate themselves: 60 days after BIA says the package is complete, 30 days after a BIA extension letter, and 15 days after each notice to compel (169.123(b), 169.304).
Service Lines: one row per home or building drop. The sheet shows when each agreement must be filed with BIA (30 days, 169.56) and flags anything overdue.
Rows marked Example show how to fill in a row. Replace or delete them.
How days are counted here
The 60-day, 30-day, and 15-day deadlines are counted as calendar days from the date you enter. Escalation deadlines are counted from the date you sent the notice; BIA may count from the date it received it, so keep proof of delivery.
NPM-TRUS-48 targets (3 and 7 business days) are counted in business days from the date BIA received the package, without holidays. The memo says it expires September 3, 2026; ask BIA whether it or a newer memo is in effect, and how it counts.
Service line filing: to be safe, the due date is 30 days after the earlier of the signing date and the installation date. Confirm with your Agency how 169.56 is counted.
A missed BIA deadline does not mean your right-of-way is approved. Use the notice-to-compel rows on the Timeline sheet.

## Tracts
Tracts on the route
One row per tract. Gray columns calculate themselves. Percent of shares: the share of trust interests whose owners signed (fee shares do not count, 169.3(c)).
Tract number | Land status | Number of owners | Consent needed (calculated) | Owners who signed | Percent of shares signed | Majority interest reached? (calculated) | 50 or more owners? (calculated) | Notes
Example: T-101 | Tribal land | 1 |  | 1 |  |  |  | Council resolution date: ____
Example: A-202 | Individually owned Indian land | 24 |  | 7 | 54% |  |  | Owner list from BIA dated ____
Example: F-303 | Fee land | 1 |  | 0 |  |  |  | Ranch owner; permission outside the BIA process

## Timeline
Timeline and BIA deadlines
Enter planned and actual dates. Gray cells calculate deadlines. A missed deadline is not an approval (169.304).
Step | Rule | Who on our team | Planned date | Actual date | Deadline or target (calculated) | Days left (calculated) | Notes
1. Map the route and list every tract | Planning
2. Written request to BIA for owner lists | 169.106
3. Survey consent and survey | 169.101
4. Tribal authorization for tribal land | 169.107(a)
5. Notice to owners and written consents for allotted land | 169.107(b)
6. Valuation or waiver | 169.110, 169.112
7. Environmental and cultural review (NEPA, Section 106, ESA) | 169.123
8. Bond or security and insurance, or waiver | 169.103
9. Package received by BIA (enter the date BIA received it) | 169.102
NPM-TRUS-48 target: package encoded, 3 business days (if the memo is in effect) | NPM-TRUS-48 |  |  | (calculated)
NPM-TRUS-48 target: completeness review, 7 business days (if the memo is in effect) | NPM-TRUS-48 |  |  | (calculated)
10. BIA letter saying the package is complete (enter the letter date) | 169.123(b)
11. BIA decision due: 60 days after a complete package | 169.123(b) |  |  | (calculated)
BIA letter asking for more time, if any (enter the letter date) | 169.123(b)
Decision due after extension: 30 days after that letter | 169.123(b) |  |  | (calculated)
Notice to compel sent to the Regional Director (enter date sent) | 169.304
Regional Director action due: 15 days | 169.304 |  |  | (calculated)
Notice to compel sent to the BIA Director (enter date sent) | 169.304
BIA Director action due: 15 days | 169.304 |  |  | (calculated)
Appeal to the Interior Board of Indian Appeals, if needed | 169.304
12. Grant approved (effective date) | 169.301
Grant recorded in the LTRO (Land Title and Records Office); copy received | 169.302
Example: if BIA's complete-package letter is dated 03/02/2026, enter it in Actual date on step 10, and the 60-day decision date shows 05/01/2026.
Formulas:
Deadline or target (calculated) = IF([Actual date, row above]="","",WORKDAY([Actual date, row above],3))
Days left (calculated) = IF([Deadline or target (calculated)]="","",[Deadline or target (calculated)]-TODAY())

## Service Lines
Service line agreements (home and building drops)
File each signed agreement and plat with BIA within 30 days (169.56). Due date = 30 days after the earlier of signing or installation, to be safe.
Home or building | Tract number | Land status | Owners, occupants, or users who signed | Tribe signed (if requested) | Date agreement signed | Date installed | Filing due, 30 days (calculated) | Date filed with BIA | Status (calculated) | Plat attached? | Notes
Example: home on Allotment A-202 | A-202 | Individually owned Indian land | Owners of record (see file) | Not requested | 2026-04-06 | 2026-04-20 |  | 2026-04-30 |  | Yes
Formulas:
Status (calculated) = IF([Filing due, 30 days (calculated)]="","",IF([Date filed with BIA]<>"",IF([Date filed with BIA]<=[Filing due, 30 days (calculated)],"Filed on time","Filed late"),IF(TODAY()>[Filing due, 30 days (calculated)],"OVERDUE","Due in "&([Filing due, 30 days (calculated)]-TODAY())&" days")))